## Sheet1
Phase | Task | Sub-Task Description | Deliverable | Duration | Timeline | Owner
Phase 1: Project Initiation & Requirement Finalization | Project Kickoff & Requirement Gathering | Conduct stakeholder meetings, finalize objectives, deliverables, timelines | MOM, Scope Doc | 5 days | 07-Oct-2025 - 11-Oct-2025 | PM, Data Science Lead
| Data Access & Infrastructure Setup | Snowflake, OASIS, ImageRight access setup, environment readiness | Access confirmation | 5 days | 10-Oct-2025 - 14-Oct-2025 | Infra, Data Team
| Identify Keys & Entity Mapping | Define NPI, Org ID, PolicyNumber, LOB mapping; confirm join logic | Entity mapping doc | 3 days | 15-Oct-2025 - 17-Oct-2025 | Data Analyst
Phase 2: Data Understanding & Profiling | Data Collection & Sampling | Receive 7-year PSL & HPL data; collect 10% sample for initial EDA | Sample dataset | 4 days | 18-Oct-2025 - 21-Oct-2025 | Data Scientist
| Data Profiling & EDA (200+ attributes) | Detect categorical vs numeric, missing values, outliers, correlations | EDA Report | 15 days | 22-Oct-2025 - 05-Nov-2025 | Data Scientist
| Data Cleaning & Validation | Imputation, transformation, consistency checks across tables | Clean dataset | 6 days | 06-Nov-2025 - 11-Nov-2025 | Data Analyst
| EDA Review with Business | Review EDA findings with actuarial team & finalize data scope | EDA Sign-off | 3 days | 11-Nov-2025 - 13-Nov-2025 | PM, SME
Phase 3: Feature Engineering | Feature Creation | Derive actuarial ratios, claim ratios, exposure, experience indicators | Feature list | 8 days | 14-Nov-2025 - 21-Nov-2025 | Data Scientist
| Attribute Standardization | Classify and standardize 200+ fields; apply categorical encoding | Feature schema doc | 5 days | 23-Nov-2025 - 27-Nov-2025 | Data Engineer
| Merge Structured & Unstructured Data | OCR extract key attributes from ImageRight docs; link with policy/claim | Unified dataset | 5 days | 28-Nov-2025 - 02-Dec-2025 | Data Engineer
Phase 4: PSL Model Development | Model Design | Define target (TOT_INC_trended), offset, training/test logic | PSL model design doc | 5 days | 02-Dec-2025 - 06-Dec-2025 | Data Scientist
| Model Training (Regression & Tree-based) | Build GLM with offset, Random Forest, XGBoost; tune hyperparameters | PSL model | 20 days | 07-Dec-2025 - 26-Dec-2025 | Data Scientist
| Model Evaluation & Validation | RMSE, MAE, R² analysis, business validation with actuaries | PSL model validation | 6 days | 01-Jan-2026 - 06-Jan-2026 | Data Scientist, SME
Phase 5: HPL Model Development | Feature Mapping & Adaptation | Reuse PSL features, add hospital KPIs (readmit rate, bed count) | HPL feature mapping | 7 days | 16-Dec-2025 - 22-Dec-2025 | Data Scientist
| Model Training (HPL) | Train regression and random forest for hospital data; tune model | HPL model | 20 days | 08-Jan-2026 - 27-Jan-2026 | Data Scientist
| Model Evaluation & Business Validation | Compare HPL vs PSL, review KPIs, validate results | HPL validation report | 6 days | 03-Feb-2026 - 08-Feb-2026 | Data Scientist, SME
Phase 6: Integration & UAT | Excel & Snowflake Integration | Integrate scoring logic into Excel pricing template and Snowflake tables | Excel-Snowflake integration | 7 days | 10-Feb-2026 - 16-Feb-2026 | ML Engineer, Data Engineer
| End-to-End Workflow Testing | Perform system UAT with business team | UAT report | 5 days | 18-Feb-2026 - 22-Feb-2026 | QA, PM
Phase 7: Documentation & Handover | Final Documentation & BRD Update | Prepare BRD, Model Doc, Data Dictionary, User Manual | Final docs | 5 days | 24-Feb-2026 - 28-Feb-2026 | Data Science Lead
| Knowledge Transfer & Sign-off | Conduct KT sessions, obtain business sign-off | Project closure MOM | 3 days | 02-Mar-2026 - 04-Mar-2026 | PM, Client

## Sheet2
Phase | Task | Sub-Task | Deliverable | Duration | Start–End | Owner
Phase 2 – Data Understanding & Profiling | Perform EDA | • Identify numerical vs. categorical attributes (250 +) | EDA summary + data type tagging | 15 days | 21 Oct – 08 Nov | Data Scientist
• Missing-value profiling / imputation rules design
• Outlier detection (boxplot & z-score)
• Correlation & multicollinearity analysis
| Validate Data Consistency | • Cross-table joins (NPI, Org ID, PolicyNumber) | Data validation log | 5 days | 09 Nov – 13 Nov | Data Analyst
• Date consistency checks (effective/expiry)
• Policy-claim linkage validation
Phase 4 – PSL Model Development | Model Design | • Define target (TOT_INC_trended + offset) | PSL model design doc | 5 days | 14 Nov – 20 Nov | Data Scientist
• Feature selection (VIF, importance ranking)
• Split train/test + sampling strategy
| Model Training | • Linear Regression with offset (GLM) | PSL model code v1 | 10 days | 21 Nov – 04 Dec | Data Scientist
• Random Forest / XGBoost experiments
• Cross-validation & hyper-parameter tuning
| Evaluation & Review | • RMSE, MAE, R² evaluation | PSL model validation report | 5 days | 05 Dec – 11 Dec | Data Scientist + Actuary
• Feature importance explanation
• Business review with SMEs
Phase 5 – HPL Model Development | Model Design / Feature Alignment | • Re-use PSL framework for hospital data | HPL feature mapping | 5 days | 24 Nov – 30 Nov | Data Scientist
• Add hospital-specific risk indicators (beds, readmit rate)
• Ensure feature schema alignment
| Model Training & Validation | • Train GLM / RF for HPL | HPL model validation report | 15 days | 01 Dec – 22 Dec | Data Scientist + Underwriter
• Evaluate vs. PSL performance
• Calibration with underwriters
Phase 6 – Integration & Testing | System Integration | • Snowflake pipeline creation | Deployed models | 7 days | 23 Dec – 31 Dec | ML Engineer
• Excel template integration for pricing simulation
• Batch scoring jobs setup
Phase 7 – Documentation & KT | Final Docs & Sign-off | • BRD update | Final deliverables & sign-off | 5 days | 02 Jan – 08 Jan | PM + Data Science Lead
• Data Dictionary (250 + fields)
• Model User Guide + KT session